## Progress Planning and Tracking
Project Name: Cybersecurity Capstone Practicum
Report Date: March 20, 2024
[5 empty] | Project Plan #1 | [5 empty] | Plan Security Program #2 |  |  |  |  | Implement Sec. Prog. #3 | [5 empty] | PenTest & Sec. Ops. #4 | [6 empty] | Presentation #5
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2024-03-12 | 2024-03-14 | 2024-03-16 | 2024-03-18 | 2024-03-20 | 2024-03-22 | 2024-03-23 | 2024-03-25 | 2024-03-27 | 2024-03-29 | 2024-03-31 | 2024-04-01 | 2024-04-03 | 2024-04-05 | 2024-04-07 | 2024-04-09 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-24 | 2024-04-26 | 2024-04-28
Project Planning | Overview | 100% |  | Masrura | 2024-03-12: 2; 2024-03-14: 2
| Team & Contact Info | 100% |  | All
| Milestones & Deliverables | 100% |  | Rick | 2024-03-14: 4; 2024-03-16: 4; 2024-03-18: 4
| Collaboration Strategy | 100% |  | Gevor | 2024-03-14: 2; 2024-03-16: 2
| Create Gantt Chart, Submit | 100% |  | Uju | 2024-03-18: 2; 2024-03-20: 5
Phase 1: Setup Security Policy | Project Update | 100% |  | Rick | 2024-03-20: 2; 2024-03-23: 2; 2024-03-27: 1
| Conduct Risk Assessment (2p) | 100% |  | Uju, Gevor | 2024-03-22: 6; 2024-03-23: 18; 2024-03-25: 3; 2024-03-27: 2
| Write Security Policies (2p) | 100% |  | Uju, Masrura | 2024-03-22: 6; 2024-03-23: 4; 2024-03-25: 20; 2024-03-27: 4
| Develop Technical Plan (3p) | 100% |  | Uju, Rick | 2024-03-22: 4; 2024-03-23: 4; 2024-03-25: 5; 2024-03-27: 24
| Update Gantt Chart, Submit | 100% |  | Uju | 2024-03-22: 2; 2024-03-25: 2; 2024-03-27: 2; 2024-03-29: 0
Phase 2: Security Implementation & Exploit Planning | Project Update | 0% |  | Rick | 2024-03-31: 2; 2024-04-01: 2
| Implement tools / updates | 0% |  | Masrura, Gevor | 2024-04-01: 20
| Implement configuration adjst. | 0% |  | Uju, Rick | 2024-04-03: 10
| Create Pentest Strategy | 0% |  | Gevor, Uju | 2024-04-05: 20
| Test Pentest Strategy on VM | 0% |  | Masrura, Gevor | 2024-04-07: 20
| Update Gantt Chart, Submit | 0% |  | Masrura | 2024-04-09: 2; 2024-04-14: 2
Phase 3: Penetration Testing & Security Operation | Project Update | 0% |  | Rick | 2024-04-14: 2; 2024-04-15: 2
| Write Executive Summary | 0% |  | Gevor | 2024-04-15: 4
| Conduct Penetration Tests | 0% |  | Gevor, Rick | 2024-04-16: 20
| Results & Recommendations | 0% |  | Rick, Gevor | 2024-04-17: 10
| Security Operations (our VM) | 0% |  | Uju, Masrura | 2024-04-18: 10
| Forensic Report (our VM) | 0% |  | Masrura, Uju | 2024-04-19: 20
| Update Gantt Chart, Submit | 0% |  | Gevor | 2024-04-20: 2
Project Summary in Final Presentation | Develop Presentation Format | 100% |  | Rick, Gevor | 2024-03-22: 6
| Record Introduction | 50% |  | Rick | 2024-03-22: 2
| Record Phase 1 Summary | 0% |  | Uju | 2024-03-31: 8
| Record Phase 2 Summary | 0% |  | Masrura | 2024-04-14: 8
| Record Phase 3 Summary | 0% |  | Gevor | 2024-04-21: 8
| Submit Presentation | 0% |  | Rick | 2024-04-22: 10
| Complete Peer Evals | 0% |  | All | 2024-04-24: 5
| Update Gantt Chart, Submit | 0% |  | Rick | 2024-04-26: 2
| Total workload | 335 |  |  | 2 | 8 | 6 | 6 | 7 | 26 | 28 | 30 | 33 | 0 | 10 | 22 | 10 | 20 | 20 | 2 | 12 | 6 | 20 | 10 | 10 | 20 | 2 | 8 | 10 | 5 | 2 | 0
Legend
Planned | 2
Delayed | 1
Number | Workload: man hour

## Sheet1
Project Name: Cybersecurity Capstone Practicum
Report Date: March 20, 2024
[5 empty] | Project Plan #1 | [5 empty] | Plan Security Program #2 |  |  |  |  | Implement Sec. Prog. #3 | [5 empty] | PenTest & Sec. Ops. #4 | [6 empty] | Presentation #5
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2024-03-12 | 2024-03-14 | 2024-03-16 | 2024-03-18 | 2024-03-20 | 2024-03-22 | 2024-03-23 | 2024-03-25 | 2024-03-27 | 2024-03-29 | 2024-03-31 | 2024-04-01 | 2024-04-03 | 2024-04-05 | 2024-04-07 | 2024-04-09 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-24 | 2024-04-26 | 2024-04-28
Project Planning | Overview | 100% |  | Masrura | 2024-03-12: 2; 2024-03-14: 2
| Team & Contact Info | 100% |  | All
| Milestones & Deliverables | 100% |  | Rick | 2024-03-14: 4; 2024-03-16: 4; 2024-03-18: 4
| Collaboration Strategy | 100% |  | Gevor | 2024-03-14: 2; 2024-03-16: 2
| Create Gantt Chart, Submit | 100% |  | Uju | 2024-03-18: 2; 2024-03-20: 5
Phase 1: Setup Security Policy | Project Update | 0% |  | Rick | 2024-03-20: 2; 2024-03-22: 2; 2024-03-23: 2
| Conduct Risk Assessment (2p) | 0% |  | Uju, Gevor | 2024-03-23: 10
| Write Security Policies (2p) | 0% |  | Uju, Masrura | 2024-03-25: 20
| Develop Technical Plan (3p) | 0% |  | Uju, Rick | 2024-03-27: 20
| Update Gantt Chart, Submit | 0% |  | Uju | 2024-03-29: 2
Phase 2: Security Implementation & Exploit Planning | Project Update | 0% |  | Rick | 2024-03-31: 2; 2024-04-01: 2
| Implement tools / updates | 0% |  | Masrura, Gevor | 2024-04-01: 20
| Implement configuration adjst. | 0% |  | Uju, Rick | 2024-04-03: 10
| Create Pentest Strategy | 0% |  | Gevor, Uju | 2024-04-05: 20
| Test Pentest Strategy on VM | 0% |  | Masrura, Gevor | 2024-04-07: 20
| Update Gantt Chart, Submit | 0% |  | Masrura | 2024-04-09: 2; 2024-04-14: 2
Phase 3: Penetration Testing & Security Operation | Project Update | 0% |  | Rick | 2024-04-14: 2; 2024-04-15: 2
| Write Executive Summary | 0% |  | Gevor | 2024-04-15: 4
| Conduct Penetration Tests | 0% |  | Gevor, Rick | 2024-04-16: 20
| Results & Recommendations | 0% |  | Rick, Gevor | 2024-04-17: 10
| Security Operations (our VM) | 0% |  | Uju, Masrura | 2024-04-18: 10
| Forensic Report (our VM) | 0% |  | Masrura, Uju | 2024-04-19: 20
| Update Gantt Chart, Submit | 0% |  | Gevor | 2024-04-20: 2
Project Summary in Final Presentation | Develop Presentation Format | 0% |  | Rick, Gevor | 2024-03-22: 6
| Record Introduction | 0% |  | Rick | 2024-03-22: 4
| Record Phase 1 Summary | 0% |  | Uju | 2024-03-31: 8
| Record Phase 2 Summary | 0% |  | Masrura | 2024-04-14: 8
| Record Phase 3 Summary | 0% |  | Gevor | 2024-04-21: 8
| Submit Presentation | 0% |  | Rick | 2024-04-22: 10
| Complete Peer Evals | 0% |  | All | 2024-04-24: 5
| Update Gantt Chart, Submit | 0% |  | Rick | 2024-04-26: 2
| Total workload | 284 |  |  | 2 | 8 | 6 | 6 | 7 | 12 | 12 | 20 | 20 | 2 | 10 | 22 | 10 | 20 | 20 | 2 | 12 | 6 | 20 | 10 | 10 | 20 | 2 | 8 | 10 | 5 | 2 | 0
Legend
Planned | 2
Delayed | 1
Number | Workload: man hour